## FS_TS Estimate
PROVINCIAL HUMAN RESOURCE MANAGEMENT AND DEVELOPMENT OFFICE (PHRMDO)
FS and TS ASSIGNMENT
Seq. Nbr. | Work Item (WI) # | FS Ref. Nbr. | TS Ref. Nbr. | Functional Description | Phase | Priority | Complexity | Group Lead | Assign Resource | FS Status | Total Est. Effort (hrs.) | FS Creation Effort (hrs.) 70% | FS Review (hrs.) 20% | FS Rework (hrs.) 10% | % Complete (FS) | FS Target Completion Date | TS Status | TS Remarks | Assign Resource | % Complete (TS) | Target Completion Date | Dependencies
1. | 00-001W | FS00-001W | TS00-001W | Position Table | 0 | 1 | Simple | Ariel | Willy |  | 10 | 7 | 2 | 1 | 0% | 07/13/2018
2. | 00-002W | FS00-002W | TS00-002W | Salary Table | 0 | 1 | Simple | Ariel | Willy |  | 10 | 7 | 2 | 1 | 0% | 07/20/2018 | [5 empty] | FS00-001W - Position Table
3. | 00-003W | FS00-003W | TS00-003W | Department | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 2018-10-07
4. | 00-004W | FS00-004W | TS00-004W | Division | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 2018-11-07 | [5 empty] | FS00-003W - Department
5. | 00-005W | FS00-005W | TS00-005W | Section | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 07/13/2018 | [5 empty] | FS00-003W - Department FS00-004W - Division
6. | 00-006W | FS00-006W | TS00-006W | Functions | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 07/16/2018
7. | 00-007W | FS00-007W | TS00-007W | Programs | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 07/18/2018
8. | 00-008W | FS00-008W | TS00-008W | Sector | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 07/20/2018
9. | 00-009W | FS00-009W | TS00-009W | Sub Sector | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 07/20/2018
10. | 00-010W | FS00-010W | TS00-010W | Source of Funds | 0 | 2 | Simple | Ariel |  |  | 10 | 7
11. | 00-011W | FS00-011W | TS00-011W | BIR Tax Table | 0 | 1 | Simple | Ariel
12. | 00-012W | FS00-012W | TS00-012W | GSIS, HDMF and SIF Contribution Table | 0 | 1 | Simple | Ariel | George |  | 10 | 7 | 2 | 1 | 0% | 07/20/2018
13. | 00-013W | FS00-013W | TS00-013W | PHILHealth Table | 0 | 1
14. | 00-014W | FS00-014W | TS00-014W | Benefits Fixed Amount - Configuration Table ( PERA, CA,CG, PEI, SA, LA, QA - Gov only) | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 07/20/2018
15. | 00-015W | FS00-015W | TS00-015W | Hazard Pay - Percentage | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 07/18/2018
16. | 00-016W | FS00-016W | TS00-016W | Sub Department | 0 | 1 | Simple | Ariel | Franklin |  | 10 | 7 | 2 | 1 | 0% | 07/18/2018
17. | 00-017W | FS00-017W | TS00-017W | RA - Representation Allowance | 0 | 1
18. | 00-018W | FS00-018W | TS00-018W | TA - Transportation Allowance | 0 | 1
19. | 00-019W | FS00-019W | TS00-019W |  | 0 | 1
20. | 00-020W | FS00-020W | TS00-020W |  | 0 | 1
21. | 00-021W | FS00-021W | TS00-021W |  | 0 | 1
22. | 00-022W | FS00-022W | TS00-022W |  | 0 | 1
23. | 00-023W | FS00-023W | TS00-023W |  | 0 | 1
24. | 00-024W | FS00-024W | TS00-024W |  | 0 | 1
25. | 00-025W | FS00-025W | TS00-025W |  | 0 | 1
26. | 00-026W | FS00-026W | TS00-026W | User Security Table(s) | 0 | 3
27. | 00-027W | FS00-027W | TS00-027W | Report Template | 0 | 3
28. | 00-028W | FS00-028W | TS00-028W | Signatories | 1
29. | 00-028W | FS00-028W | TS00-028W | Personal Data Sheet - excluding Trainings which will be part of Phase 3 Development | 1
30. | 00-029W | FS00-029W | TS00-029W | PDF Entry per Position | 1
31. | 01-001W | FS01-001W | TS01-001W | Appointment for Regular, Casual and Job Order | 1
32. | 01-002W | FS01-002W | TS01-002W | CSC 33-B - Permanent Appointment | 1
33. | 01-003W | FS01-003W | TS01-003W | PDF - DBM-CSC Form - 1 per Appointee | 1
34. | 01-001R | FS01-001R | TS01-001R | CSC 32 - Oath of Office | 1
35. | 01-001R | FS01-001R | TS01-001R | CSC 4 - Certification of Assumption to Duty | 1
36. | 01-002R | FS01-002R | TS01-002R | CATS # 5137 Job Order Appointment for Special Cases | 1
37. | 01-003R | FS01-003R | TS01-003R | CATS # 1412 Job Order Appointment Generic with existing system | 1
38. | 01-004R | FS01-004R | TS01-004R | CSC Form - 1 Report on Appointment Issued (RAI) | 1
39. | 01-005R | FS01-005R | TS01-005R | Report of Accession | 1
40. | 01-006R | FS01-006R | TS01-006R | Report of Separation
25. | 01-007R | FS01-007R | TS01-007R | Certification of Erasure/Alteration
26. | 01-008R | FS01-008R | TS01-008R | DiBar Report
27. | 01-009R | FS01-009R | TS01-009R | Certificate of employment
28. | 01-010R | FS01-010R | TS01-010R | Certificate of employment with compensation
29. | 01-010R | FS01-010R | TS01-010R | Certificate of employment Oneness
30. | 01-011R | FS01-011R | TS01-011R | Certificate of No Pending Admin Case
31. | 01-012R | FS01-012R | TS01-012R | Agency Remittance Advice for GSIS - FORM A
32. | 01-013R | FS01-013R | TS01-013R | Agency Remittance Advice for GSIS - FORM B
33. | 01-014R | FS01-014R | TS01-014R | Agency Remittance Advice for GSIS - FORM C
34. | 01-015R | FS01-015R | TS01-015R | Agency Remittance Advice for GSIS - FORM D
35. | 01-016R | FS01-016R | TS01-016R | Agency Remittance Advice for GSIS - FORM E
36. | 01-017R | FS01-017R | TS01-017R | Manpower Complement (DILG)
37. | 01-018R | FS01-018R | TS01-018R | IGHRS for CSC
38. | 01-019R | FS01-019R | TS01-019R | Service Record (Regular and Casual)
39. | 01-020R | FS01-020R | TS01-020R | List of Employees (Regular, Casual and/or Job Order)
40. | 01-022R | FS01-022R | TS01-022R

## FS Progress Tracker
PROVINCIAL HUMAN RESOURCE MANAGEMENT AND DEVELOPMENT OFFICE (PHRMDO)
FS and TS TRACKER
Seq. Nbr. | Work Item (WI) # | FS Ref. Nbr. | TS Ref. Nbr. | Functional Description | Assign To | Status | Est. Effort (hrs.) | Start Date | End Date | Peer Review |  |  | PL Review |  |  | DM Review
[10 empty] | Target Review Date | Actual Review Date | Reviewer | Target Review Date | Actual Review Date | Reviewer | Target Review Date | Actual Review Date | Reviewer
1. | 00-001W | FS00-001W | TS00-001W | Position Table | Willy | PL Review | 10 | 2018-09-07 | 07/13/2018 | 2018-12-07 |  | Franklin | 2018-12-07 |  | Joyzel / Ariel | 07/13/2018 |  | Joyzel / Ariel
2. | 00-002W | FS00-002W | TS00-002W | Salary Table | Willy | Peer Review | 10 | 07/16/2018 | 07/20/2018 | 07/19/2018 |  | Franklin | 07/19/2018 |  | Joyzel / Ariel | 07/13/2018 |  | Joyzel / Ariel
3. | 00-003W | FS00-003W | TS00-003W | Department | Franklin | Peer Review | 10 | 2018-09-07 | 2018-10-07 | 2018-10-07 | 2018-11-07 | Willy | 2018-10-07 |  | Joyzel / Ariel | 2018-10-07 |  | Joyzel / Ariel
4. | 00-004W | FS00-004W | TS00-004W | Division | Franklin | Peer Review | 10 | 2018-10-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | Willy | 2018-11-07 |  | Joyzel / Ariel | 2018-11-07 |  | Joyzel / Ariel
5. | 00-005W | FS00-005W | TS00-005W | Section | Franklin | PL Review | 10 | 2018-12-07 | 07/13/2018 | 07/13/2018 | 07/16/2018 | George | 07/13/2018 |  | Joyzel / Ariel | 07/13/2018 |  | Joyzel / Ariel
6. | 00-006W | FS00-006W | TS00-006W | Functions | Franklin | Peer Review | 10 | 07/13/2018 | 07/16/2018 | 07/16/2018 | 07/16/2018 | Willy | 07/16/2018 |  | Joyzel / Ariel | 07/16/2018 |  | Joyzel / Ariel
7. | 00-007W | FS00-007W | TS00-007W | Programs | Franklin | PL Review | 10 | 07/17/2018 | 07/18/2018 | 07/18/2018 | 07/16/2018 | George | 07/18/2018 |  | Joyzel / Ariel | 07/18/2018 |  | Joyzel / Ariel
8. | 00-008W | FS00-008W | TS00-008W | Sector | Franklin | Peer Review | 10 | 07/19/2018 | 07/20/2018 | 07/20/2018 | 07/16/2018 | Willy | 07/20/2018 |  | Joyzel / Ariel | 07/20/2018 |  | Joyzel / Ariel
9. | 00-009W | FS00-009W | TS00-009W | Sub Sector | Franklin | Peer Review | 10 | 07/19/2018 | 07/20/2018 | 07/20/2018 | 07/16/2018 | Willy | 07/20/2018 |  | Joyzel / Ariel |  |  | Joyzel / Ariel
10. | 00-010W | FS00-010W | TS00-010W | Source of Funds |  | Not Started | 10
11. | 00-011W | FS00-011W | TS00-011W | BIR Tax Table |  | Not Started | 10 | 07/17/2018 | 07/18/2018
12. | 00-012W | FS00-012W | TS00-012W | GSIS, HDMF and SIF Contribution Table | George | In Progress | 10 | 07/16/2018 | 07/20/2018 | 7/19/2018 |  | Willy | 07/19/2018 |  | Joyzel / Ariel | 07/20/2018
13. | 00-013W | FS00-013W | TS00-013W | PHILHealth Premium Contribution Table | Ariel/Franklin | In Progress | 10
14. | 00-014W | FS00-014W | TS00-014W | Benefits Fixed Amount - Configuration Table (PERA, CA,CG, PEI, SA, LA, QA - Gov only) | Ariel/Franklin | In Progress | 10 | 07/17/2018 | 07/18/2018
15. | 00-015W | FS00-015W | TS00-015W | Hazard Pay - Percentage | Franklin | In Progress | 10 | 07/16/2018 | 07/17/2018
16. | 00-016W | FS00-016W | TS00-016W | Sub Department | Willy | In Progress | 10 | 07/13/2018 | 07/16/2018 | 07/16/2018 |  | Franklin | 07/16/2018
17. | 00-017W | FS00-017W | TS00-017W | RA - Representation Allowance | Ariel/Franklin | In Progress | 10 | 07/17/2018 | 07/18/2018
18. | 00-018W | FS00-018W | TS00-018W | TA - Transportation Allowance | Ariel/Franklin | In Progress | 10 | 07/17/2018 | 07/18/2018
19. | 00-019W | FS00-019W | TS00-019W
20. | 00-020W | FS00-020W | TS00-020W
21. | 00-021W | FS00-021W | TS00-021W
22. | 00-022W | FS00-022W | TS00-022W
23. | 00-023W | FS00-023W | TS00-023W
24. | 00-024W | FS00-024W | TS00-024W
25. | 00-025W | FS00-025W | TS00-025W
26. | 00-026W | FS00-026W | TS00-026W | User Security Table(s)
27. | 00-027W | FS00-027W | TS00-027W | Report Template
28. | 00-028W | FS00-028W | TS00-028W | Signatories
29. | 00-028W | FS00-028W | TS00-028W | Personal Data Sheet - excluding Trainings which will be part of Phase 3 Development
30. | 00-029W | FS00-029W | TS00-029W | PDF Entry per Position
31. | 01-001W | FS01-001W | TS01-001W | Appointment for Regular, Casual and Job Order
32. | 01-002W | FS01-002W | TS01-002W | CSC 33-B - Permanent Appointment
33. | 01-003W | FS01-003W | TS01-003W | PDF - DBM-CSC Form - 1 per Appointee
34. | 01-001R | FS01-001R | TS01-001R | CSC 32 - Oath of Office
35. | 01-001R | FS01-001R | TS01-001R | CSC 4 - Certification of Assumption to Duty
36. | 01-002R | FS01-002R | TS01-002R | CATS # 5137 Job Order Appointment for Special Cases
37. | 01-003R | FS01-003R | TS01-003R | CATS # 1412 Job Order Appointment Generic with existing system
38. | 01-004R | FS01-004R | TS01-004R | CSC Form - 1 Report on Appointment Issued (RAI)
39. | 01-005R | FS01-005R | TS01-005R | Report of Accession
40. | 01-006R | FS01-006R | TS01-006R | Report of Separation
25. | 01-007R | FS01-007R | TS01-007R | Certification of Erasure/Alteration
26. | 01-008R | FS01-008R | TS01-008R | DiBar Report
27. | 01-009R | FS01-009R | TS01-009R | Certificate of employment
28. | 01-010R | FS01-010R | TS01-010R | Certificate of employment with compensation
29. | 01-010R | FS01-010R | TS01-010R | Certificate of employment Oneness
30. | 01-011R | FS01-011R | TS01-011R | Certificate of No Pending Admin Case
31. | 01-012R | FS01-012R | TS01-012R | Agency Remittance Advice for GSIS - FORM A
32. | 01-013R | FS01-013R | TS01-013R | Agency Remittance Advice for GSIS - FORM B
33. | 01-014R | FS01-014R | TS01-014R | Agency Remittance Advice for GSIS - FORM C
34. | 01-015R | FS01-015R | TS01-015R | Agency Remittance Advice for GSIS - FORM D
35. | 01-016R | FS01-016R | TS01-016R | Agency Remittance Advice for GSIS - FORM E
36. | 01-017R | FS01-017R | TS01-017R | Manpower Complement (DILG)
37. | 01-018R | FS01-018R | TS01-018R | IGHRS for CSC
38. | 01-019R | FS01-019R | TS01-019R | Service Record (Regular and Casual)
39. | 01-020R | FS01-020R | TS01-020R | List of Employees (Regular, Casual and/or Job Order)
40. | 01-022R | FS01-022R | TS01-022R